## 2025
# | Industry | Domain | Employer | Role | Project Name | Project Code | Key Result | Client | Technology | Start | End | Situation | Task | Action | Result
1 | Telecom | Finance | Rostelecom.SkyLink | Business Analyst, Project Manager | Financial Monitoring | SKY-BARS | Automated internal financial control system. Implemented a budgeting and control process that reduced the budget preparation cycle from 6 months to 2 and improved financial transparency. | Rostelecom.SkyLink | Microsoft C#, MS SQL Server, MS SQL Analysis Services, MS SQL Reporting Services. | 2008-08-01 | 2010-08-01 | The company lacked a financial planning and budget control system. Budgeting was done in Excel, which was time-consuming, error-prone, and difficult to manage across multiple regional branches. | As the IT Project Manager and Business Analyst, I was responsible for delivering a solution to support automated financial planning, budget approval, and budget control processes across the enterprise. | I oversaw the project delivery, ensuring timely progress within budget and scope. I coordinated stakeholder engagement, gathered requirements, supervised development, participated in regional rollouts, and validated results during acceptance testing. | The company implemented a budgeting and control process, reducing the budgeting cycle from 6 months to 2. Financial management became more transparent, decision-making more predictable, and reporting more consistent and comprehensible.
2 | Telecom | Accounting, Retail | Rostelecom.SkyLink | Business Analyst, Project Manager | 1С: Accounting + Trade & Warehouse | SKY-ACC-TRD | Deployed and configured integrated accounting. Unified accounting and inventory management across all legal entities, enabling transparent reporting and integration with planning systems. | Rostelecom.SkyLink | 1C:Accounting, 1C:Trade&Warehouse | 2008-08-01 | 2010-08-01 | The company lacked a unified accounting system. Financial data was fragmented across multiple legal entities with different accounting policies. The prior project (budget planning) demanded integration with a standardised accounting platform. | Act as IT Project Manager and Business Analyst to oversee the implementation of unified accounting (1C:Accounting) and retail inventory (1C:Trade & Warehouse) systems. | Led the implementation and acted as liaison with stakeholders across legal entities. Collected and harmonised diverse requirements, oversaw customisation of 1C to fit a complex corporate structure, and validated solutions through business acceptance testing. | A unified accounting and inventory system was launched, enabling consolidated reporting across all branches. Reporting became timely and transparent, and accounting policies were streamlined across the organisation.
3 | Telecom | C&B, HR | Rostelecom.SkyLink | Business Analyst, Project Manager | 1С: Payroll & HR | SKY-ZUP | Introduced a single payroll and motivation system across all branches, integrated with the budgeting system. Launched HR system for 50+ users. | Rostelecom.SkyLink | 1C:Salary and HR Management, integrated with the BARS budgeting system. | 2008-08-01 | 2010-08-01 | The company had grown through mergers and acquisitions and was composed of multiple branches and legal entities. There was no unified payroll or motivation system across the organisation. | The company had grown through mergers and acquisitions and was composed of multiple branches and legal entities. There was no unified payroll or motivation system across the organisation. | I collected requirements, managed timelines and quality, coordinated meetings and project activities, and ensured proper handover of the project to the business owner. I also oversaw integration with the budgeting system (Project #1). | A clear and unified payroll and motivation system was implemented across all branches. The project introduced a new reporting system and integrated payroll with the company's budgeting solution (BARS).
4 | Telecom | ERP | Rostelecom.SkyLink | Solution Architect, Project Manager, MS Dynamics Administrator | ERP Implementation (Microsoft Dynamics AX) | SKY-DAX | The company gained transparency and timely access to operational data through a unified ERP system. ERP Integrated with Billing and launched a Helpdesk. Standardised landscape and organised transparent reporting, increasing business manageability during the company's pre-sale phase. | Rostelecom.SkyLink | MS Dynamics AX + Integration + HelpDesk | 2008-08-01 | 2010-08-01 | The company had a complex legal and organisational structure and was preparing for acquisition. It lacked transparency in its reporting and needed to unify its information landscape to improve manageability and data consistency. | I served as the Project Manager and Business Analyst. My task was to ensure the project progressed on schedule and met the strategic needs of the organisation for transparent reporting and unified systems. | I organised and oversaw project activities, implemented a system of weekly progress reporting for company leadership, and coordinated work across departments to align processes with the ERP implementation. | The company successfully established optimised and unified processes, significantly improving the quality and timeliness of business information, thus increasing overall enterprise transparency and control.
5 | Oil & Gas | Card Processing, Retail, Fuel Retail | OilPC | Project Manager, Business Analyst, Solution Architect | B2B Fuel Payment System | OILPC-KSBR | Created a platform for cashless settlement. Reduced fraud by replacing paper fuel coupons with cards. Automated cashless settlements with 70,000 legal entities; reduced reconciliation time 6x, cut fraud losses 10x; received a client commendation. | Gazprom Neft | Java, PHP, Oracle DB | 2012-01-01 | 2015-07-31 | Gazprom Neft operated a large network of gas stations and worked with both individuals and over 70,000 corporate clients. Fuel was provided to corporate clients via prepaid cards and paper vouchers, leading to reconciliation errors and opportunities for fraud. | To develop and implement a fuel settlement system based on smart chip cards processed through OilPC’s proprietary processing network. The goal was to replace paper vouchers, reduce fraud, and enable seamless cashless transactions for corporate clients at Gazprom Neft gas stations. | Led a cross-functional team of up to 22 people, including subcontractors. Collected and analyzed business requirements, worked on UI/UX design, and performed business analysis. Organized and conducted demos and acceptance testing. Ensured proper coordination across multiple vendor teams. | The system enabled accurate and transparent reconciliation with over 70,000 corporate clients. Time to reconcile was reduced 6x (from 6 weeks to 1 week), fraud losses were cut 10x, and client satisfaction improved due to a more reliable settlement process. Received an official letter of gratitude from the client.
6 | Oil & Gas | Card Processing, Retail, Fuel Retail | OilPC | Business Analyst, Project Manager, Solution Architect | Loyalty Program for Fuel Retail | OILPC-LOY | Designed and launched a loyalty system for the fuel retail chain. Implemented a comprehensive loyalty program platform. Participants grew from 1M to 4.5M; marketing effectiveness significantly improved. | Gazprom Neft | Java, PHP, Oracle DB | 2012-02-01 | 2015-08-31 | Gazprom Neft operated a loyalty program that was underdeveloped. While loyalty cards had been issued, there was no ability to create or manage promotions, segment customers, target campaigns, analyze consumer behavior, or detect fraud. The loyalty program was essentially non-functional. | The task was to build a system for managing the full lifecycle of loyalty campaigns — from customer behavior analysis and segmentation to campaign planning, execution, and post-analysis. The system needed to support compliance with local laws and handle both fuel and non-fuel products. | I led the project as Project Manager, overseeing timelines and optimal use of resources. I also acted as Business Analyst — gathering requirements, managing change requests, drafting technical specifications, and coordinating demos and acceptance testing with the client. | The client gained a fully operational loyalty management system, enabling strategic planning and targeted campaign execution. Customer loyalty significantly increased — program participation grew from 1 million to 4.5 million users. The company also gained better control, reduced fraud, and improved ROI on promotional spending.
7 | Healthcare | Workflow Automation | FMBA | Project Manager, Business Analyst | Medical Information System (MIAS) | FMBA-MIAS | Delivered a medical analytics system for FMBA to forecast athletes' performance and support training plans based on health assessments. | The Federal Medical-Biological Agency (FMBA) | Mongo DB, Ruby, Rabbit MQ | 2012-03-01 | 2015-09-30 | Medical check-up data for Olympic athletes was stored on paper, making it difficult to analyze and impossible to predict performance based on medical history. | The goal was to develop an information system for storing and analyzing medical records and forecasting athletic performance, replacing manual processes and enabling strategic training decisions. | Led the project as both Project Manager and Scrum Master. Introduced Scrum for the first time, gathered requirements from diverse stakeholders, designed interfaces, managed development, organized demos and acceptance testing, and oversaw data migration from paper. | The Federal Medical-Biological Agency (FMBA) received a digital platform for managing and analyzing athlete check-up data. It enabled performance forecasting and helped coaches plan training more effectively.
8 | Oil & Gas | Business Analysis | Gamma | System Analyst | Fuel Retail Management System | GAM-NAMOS | An architecture audit of the existing, already implemented fuel retail management system (Namos) at petrol stations was performed. Documentation for the existing software was created in accordance with local and European standards. | Wincor Nixdorf | Confluence | 2012-04-01 | 2015-10-31 | Wincor Nixdorf had implemented a system for managing fuel station operations (Namos platform) and required a comprehensive review of its architecture and compliance documentation to align with both Russian and European standards. | Conduct a system audit and documentation analysis to evaluate the implementation, identify compliance gaps, and produce standardised project documentation in line with local (GOST) and international norms. | Assessed the deployed system's architecture and operational components. Collected and analysed existing technical and user documentation. Aligned system documentation with GOST and relevant European standards. Prepared formal project documentation packages to ensure regulatory and procedural compliance. | Delivered a full set of compliant technical documents, improving the transparency and maintainability of the fuel station management system. Enabled the client to validate the implementation and prepare for potential enhancements or audits.
9 | Transport | Fleet Management, AWS, Cloud | Gamma | Solution Architect, PM | Fleet Management | GAM-CAR5 | Delivered an integrated carsharing management system from scratch, including infrastructure migration to AWS Cloud, significantly improving transparency and system reliability. | CAR5 | PHP, Web, 1C, AWS Cloud | 2015-07-31 | 2017-02-28 | CAR5, a client of Gamma, needed a modernized gas station management system. The legacy system was outdated, lacked integration capabilities, and failed to provide transparency and control over retail operations. | The goal was to implement a new gas station management system based on 1C, with full data migration, integration with existing infrastructure, and complete setup of all retail points. | I acted as both the Solution Architect and Project Manager. I led requirements gathering, designed the system architecture, managed integration with legacy systems, supervised data migration, coordinated setup of POS terminals, and ensured successful go-live at all locations. | The client received a fully integrated, reliable gas station management system, improving operational transparency, reducing system failures, and enhancing overall efficiency and control.
10 | Retail | IoT, Food Retail | Gamma | Enterprise Architect | IoT + Big Data for the Retail Chain | GAM-X5 | The client received a chosen architectural solution and a clear roadmap, laying the foundation for significant savings. | X5 | IoT, Big Data, BI | 2015-08-31 | 2015-12-31 | Client: X5 Retail Group (a large retail chain) Employer: Gamma X5 Retail Group faced the challenge of ineffective temperature control in refrigerators and rooms across its numerous retail locations. This led to significant product losses due to thawing, high electricity costs, and unpredictable equipment breakdowns. The absence of a system for predictive analysis and planned maintenance exacerbated these issues, resulting in frequent unscheduled repairs and operational downtime. | In my dual role as Enterprise Architect and Solution Architect, my task was to develop a comprehensive architectural solution for X5 Retail Group. The solution aimed to: monitor temperatures in refrigerators and premises, predict climate equipment failures, and plan maintenance and repairs. A key metric for success was to achieve a 10% reduction in electricity costs. My involvement in the project was to conclude with the preparation of all necessary documentation for launching a tender for the project's implementation. | To address these tasks, I undertook the following actions over a period of 2 months: In-depth Stakeholder Requirements Gathering: I conducted numerous meetings with diverse stakeholders from various departments within X5 Retail Group. A significant challenge was the heterogeneity of opinions and requirements among the many participants, necessitating meticulous coordination and consideration of each viewpoint to form a unified project vision. Market Research and Vendor Analysis: I thoroughly researched and evaluated offerings from various vendors (such as Danfoss, Fender, and others) specializing in monitoring and predictive maintenance systems. Development of Vendor Evaluation System: I created a structured methodology for objectively assessing potential suppliers and their products, based on technical specifications, cost-effectiveness, and implementation experience. Development of Two Architectural Solution Options: Based on the gathered requirements and market analysis, I designed two alternative, yet fully detailed, architectural solutions. These solutions included: Sensors: For collecting temperature and equipment status data. In-store Hubs: For aggregating data from local sensors within each retail outlet. Centralized Control Panel: For collecting and processing information from the hubs, integrated with equipment from various vendors. Centralized Data Storage: For accumulating and storing all operational and analytical information. Business Intelligence System: For performing predictive analytics (forecasting breakdowns) and optimizing maintenance planning. Economic Justification and Presentation: I presented the developed solution options to the client (X5 Retail Group), providing a detailed rationale for each, including projected economic benefits and strategies to achieve the 10% reduction in energy consumption. Roadmap Formulation: I developed a clear and phased Roadmap for the implementation of the chosen solution and prepared all necessary materials for the subsequent tendering process. | As a result of my work, X5 Retail Group gained: Two Fully Developed Architectural Solutions and Detailed Vendor Analysis: The client received a comprehensive overview of potential implementation paths and objective information to make an informed decision. A Clear Project Roadmap: A concrete, step-by-step roadmap was established, providing the company with certainty and the ability to proceed to the practical step of launching a tender for the project's execution. Justification of Potential Economic Efficiency: The client received confirmation of significant projected savings: Up to a 10% reduction in electricity costs through optimized temperature regulation. Minimization of product losses due to thawing. Optimization of maintenance and repair costs through predictive planning. My work successfully concluded at the stage of preparing the company for the tender announcement, providing a complete and clear foundation for the project's subsequent implementation.
11 | Finance | Digital Marketing | Gamma | Business Analyst, Project Manager | Omnichannel Communications | GAM-VTB | The system successfully sent hundreds of thousands of messages per week, reduced message preparation time by 10 times, and enabled event-based mailings to be completed in one day, significantly enhancing communication efficiency and quality. | VTB Pension Fund | Web, PHP | 2015-12-31 | 2018-07-31 | VTB Pension Fund faced significant challenges in managing client communications. Their existing mailing system was inefficient and unsystematic, making it impossible to correctly and timely send out large volumes of information. There was no unified mailing list, client segmentation, or defined communication scenarios, leading to the team being "confused" by processes and operating without a clear strategy. This hindered accurate and timely client updates regarding their personal accounts and related events. | In my dual role as Business Analyst and Project Manager, my task was to develop and implement an integrated solution for an omnichannel communication system. The objective was to ensure the ability to timely and accurately inform clients about their account status and related events. This required creating a system capable of omnichannel communication using the client's Personal Account, email, and SMS, while maintaining a consistent communication style and strategy. | To achieve these goals, I undertook the following actions over a period of two years and seven months (from December 2015 to July 2018, including subsequent system enhancements): Project Organization and Planning: I initiated and structured the project, defining its scope and objectives. Stakeholder Identification and Engagement: I identified all key project stakeholders within VTB Pension Fund and actively engaged with them throughout the entire process. Requirements Gathering and Analysis: In my role as Business Analyst, I delved deeply into the business needs, gathering and analyzing stakeholder requirements while considering all existing business rules and constraints (both technical and legal). Software Development Process Management: I organized the entire software development process, built the development team, and oversaw their work, ensuring that the developed solution met requirements and quality standards. The development utilized Web, PHP, and C# technologies. Oversight of Development and Implementation Accuracy: I maintained continuous oversight of the development progress and the correct implementation of the system. Project Delivery and Acceptance: I successfully presented and delivered the project to the client, receiving formal commendation for the work completed. | As a result of my work, the client gained: A Robust and Scalable Omnichannel Communication System: The system was successfully implemented and began processing hundreds of thousands of messages per week. Significant Reduction in Message Preparation Time: The time required to prepare messages for distribution was reduced tenfold. Accelerated Event-Based Mailings: Information dissemination for a single event, which previously took up to two weeks, is now completed within one day. High Quality and Reliability of Mailings: Messages are now sent without errors and without blocking by mail services. Unified Communication Strategy: The client's team learned to use templates and established a systematic approach to client communication across three key channels (Personal Account, Email, SMS) with a consistent style and strategy. High Client Satisfaction: The client expressed deep satisfaction with the ability to effectively and consistently inform clients, leading to increased client loyalty and satisfaction.
12 | Oil & Gas | Loyalty Program, Retail | Gamma | Solution Architect, Project Manager | Fuel Station Management System | GAM-ZG | Implemented fuel station system with integration and migration. (Тут надо обновить чтобы была еще программа лояльности) | ZG Fuel Retail Chain | PHP, 1C | 2015-01-01 | 2019-12-01 | Zmey Gorynych' Gas Station Network likely faced the need to modernize or replace their existing fuel station management system. This could have been due to the inefficiency of the current solution, a lack of necessary functionalities, difficulties with integration with other business systems, or the need to migrate data from an older platform to enhance operational efficiency and manageability of the network. | In my roles as Solution Architect and Project Manager, my task was to implement a new fuel station management system for the Zmey Gorynych Gas Station Network. This included designing the solution, its implementation, ensuring necessary integration with other systems, and successfully migrating data from the old platform to the new one. The ultimate goal was to enhance overall operational efficiency and provide modern capabilities for managing the gas station network. | To achieve these goals, I undertook the following actions over a period of 5 years (from January 2015 to December 2019): Requirements Gathering and Analysis: Conducted a detailed collection and analysis of business requirements for the new FSMS, including functionalities for fuel inventory management, sales, payments, personnel, and reporting. Solution Architecture Design: As Solution Architect, I developed a comprehensive architecture for the FSMS, defining modules, their interactions, and necessary integrations. PHP and 1C technologies were utilized in development. Managed Development and Implementation Project: As Project Manager, I was responsible for all aspects of project management: planning, task allocation, risk management, timeline, and budget control. I led the team of developers and other specialists throughout all stages of the project lifecycle, including development, testing, and implementation. Integration with Existing Systems: Organized and oversaw efforts to integrate the new FSMS with other internal and external client systems (e.g., accounting systems, loyalty programs, payment terminals). Data Migration Planning and Execution: Developed a strategy for data migration from the old platform to the new one, and managed the process of data extraction, transformation, and loading, ensuring data integrity and accuracy. System Setup and Configuration: Supervised the setup and configuration of the system in accordance with the business processes of the Zmey Gorynych Gas Station Network. Testing, Training, and Launch: Organized comprehensive system testing, end-user training, and the subsequent phased launch of the platform into production across all gas stations in the network. | As a result of my work, the client gained: Successfully Implemented Fuel Station Management System: The Zmey Gorynych Gas Station Network received a modern and efficient tool for managing its operations. Comprehensive Integration Achieved: The new system was successfully integrated with all necessary internal and external services, ensuring a seamless data flow. Data Migration Completed: All historical and current data were successfully migrated to the new platform, allowing for continuity of operations and analysis. Enhanced Operational Efficiency: Automation and centralization of processes led to increased efficiency in FSMS management and reduced manual operations. Improved Network Manageability: Management gained more transparent and complete control over all aspects of gas station operations.
13 | Telecom | Data Analytics, Digital Marketing | Rostelecom.Restream | Business Analyst | Proteus - Data Management System (Traffic analyser, segmentation, targeting, recommendation) | RTK-PROTEUS | The system was launched and as a result allowed the creation of a new business within the company, generating additional profit, and provided capabilities for targeted advertising messages and a recommendation system. | Rostelecom.Restream | Web, Cisco, Java | 2016-09-01 | 2018-09-01 | Rostelecom.Restream's management set the task of increasing company profits. One chosen path was to place advertising on the company's resources. This advertising needed to be targeted at specific user segments, which required deep analysis of user traffic and interests. | To achieve the goal of increasing profit, it was decided to analyze the traffic of users utilizing terrestrial internet. It was necessary to segment users, perform identity resolution, segment users further, and then extract a graph of their interests. Additionally, a system for targeting advertising messages and a recommendation system needed to be developed. | In my role as Project Manager and Business Analyst, I undertook the following actions over a period of 2 years (from September 2016 to September 2018): Project Management: I led the project through all its stages, ensuring timely task completion and coordination of team efforts. Stakeholder Interaction: I conducted regular meetings with key stakeholders to identify, gather, clarify, and validate system requirements. Requirements Identification and Formalization: I thoroughly elaborated on the functional and non-functional requirements for modules involving traffic analysis, identity resolution, user segmentation, interest graph construction, ad targeting, and the recommendation system. Subcontractor Management: I coordinated the work of engaged subcontractors, controlled the quality of their deliverables, and managed their integration with the overall project. Solution Description Preparation: Based on the gathered and validated requirements, a detailed description of the system's architecture and functionality was prepared and handed over for implementation. | As a result of my work: The System was Successfully Launched: A comprehensive system for traffic analysis, segmentation, and targeting was created and implemented. New Business Created: The system enabled the company to establish a new business line related to targeted advertising placement. Additional Profit Generated: The launch of the advertising platform led to a significant increase in company profits. Targeting and Recommendation Capabilities Developed: The system provided functionality for precise targeting of advertising messages and delivering personalized recommendations to users. Increased Value of Company Resources: The company's resources became more attractive to advertisers due thanks to advanced targeting capabilities.
14 | Telecom | Analytics | Rostelecom.Restream | Business Analyst | Interface layer (information presentation system, data marts) | RTK-DASH | Analysis and audit of the existing solution were performed, and documentation for changes to the information presentation system and data marts was prepared. | Rostelecom.Restream | Big Data, BI, DWH | 2016-10-01 | 2018-10-01 | Rostelecom.Restream, as a large telecommunications company, likely faced challenges in effectively presenting and accessing its data. The absence of an optimized interface layer or data marts could have led to difficulties for business users in obtaining necessary analytics, slow report performance, or an incomplete picture of operational activities. The existing solution might have been outdated, inefficient, or not aligned with current business needs. | In my role as Business Analyst, my task was to conduct an analysis and audit of the existing interface layer and data mart systems. The goal was to identify problems, define needs for changes, and prepare detailed documentation that would serve as a basis for their implementation. This was intended to improve the accessibility and quality of information for business decision-making. | To achieve these goals, I undertook the following actions over a period of 2 years (from October 2016 to October 2018): Gathered and Analyzed Current State: Conducted a detailed study of the current information presentation system and data marts, including their architecture (Big Data, BI, DWH), utilized technologies, data loading and processing procedures, and functionality available to end-users. Stakeholder Interaction: Held interviews and workshops with various business units (marketing, sales, finance, technical departments) to understand their data needs, challenges with the existing system, and expectations for changes. Solution Audit: Performed an audit of the current solution, identifying bottlenecks, inefficiencies, data errors, performance issues, and missing functional capabilities. Formulated Requirements for Changes: Based on the conducted analysis and audit, I formulated clear, detailed requirements for changes to the system. This included requirements for new data marts, modifications to existing ones, performance improvements, expansion of BI reporting functionality, etc. Prepared Documentation: Developed a complete set of documentation for the changes, which included: functional specifications, data schemas, data flow descriptions, user scenarios, and recommendations for system optimization and refinement. This documentation was intended to serve as a guide for the development team. Documentation Alignment: Presented and aligned the developed documentation with all key stakeholders, including business owners and technical teams, to ensure a unified understanding and acceptance of the proposed changes. | As a result of my work: Comprehensive Analysis and Solution Audit Performed: The company gained a deep understanding of the state of its interface layer and data marts, as well as identified problems and potential improvements. Exhaustive Documentation for Changes Prepared: A detailed package of documents was created, serving as a clear guide for further development and modification of the information presentation system. Foundation Laid for Improved Data Accessibility: The groundwork was laid for enhancing the efficiency of business users' access to necessary information, which should contribute to faster and more informed management decisions. Improved Interaction Between Business and IT Departments: Clearly formulated and agreed-upon requirements facilitated more effective collaboration between departments. Reduced Risks in Future Enhancements: The availability of current and complete documentation reduces the risks of errors and rework in subsequent phases of system development.
15 | Oil & Gas | Data Management | Rostelecom.Restream | Business Analyst | Data Lake (Presale) | RTK-LAKE | Successfully conducted a presale for a large oil and gas enterprise, including analyzing customer requirements, proposing and presenting a solution, and defending it in a competition. | Gazprom Neft |  | 2016-11-01 | 2018-11-01 | Gazprom Neft faced a pressing need for the efficient storage and analysis of massive, heterogeneous datasets related to fuel supplies and sales, as well as associated products. Existing systems struggled with this volume and variety, hindering the extraction of valuable business insights and impeding the discovery of new profit growth opportunities. | In my role as a Business Analyst, my primary task was to conduct a presale for Gazprom Neft on the concept of a "Data Lake." This involved analyzing customer requirements, developing and proposing an optimal solution, presenting it, and successfully defending it in a competitive tender. The ultimate aim of the proposed Data Lake solution was to help Gazprom Neft uncover additional profit growth opportunities through insights gained from comprehensive processing of this big data. | To achieve these goal, I undertook the following actions over a period of 2 years (from November 2016 to November 2018): Deep Customer Needs Analysis: Conducted a comprehensive analysis of Gazprom Neft's business processes and existing systems to identify key data needs, challenges with current storage, and expectations for a "Data Lake." Special attention was paid to data regarding fuel supplies, sales, and related products. Developed Data Lake Solution Concept: Based on the identified requirements, I developed a detailed "Data Lake" solution concept, including architecture (data sources, loading methods, storage, processing, consumption), technology stack, and potential business cases for the oil and gas industry. Prepared Technical and Commercial Proposal: Compiled a comprehensive technical and commercial proposal outlining the proposed solution, its benefits, implementation phases, and estimated costs. Prepared and Delivered Presentation: Developed presentation materials and conducted a series of presentations of the solution for various levels of Gazprom Neft's management and technical specialists, emphasizing business value and technological advantages. Defended Solution in Tender: Actively participated in tender procedures, including preparing responses to questions, clarifying solution details, and defending it before the tender commission, demonstrating a deep understanding of client needs and expertise in the proposed area. Collaborated with Experts: Engaged technical experts and architects for in-depth design and to answer complex technical questions during the presale phase. Formulated Value Proposition: Prepared arguments for ROI (Return on Investment) and business benefits that the "Data Lake" could bring to the client, such as improved analytics, cost reduction, and accelerated processes. | As a result of my work: A Successful Presale was Conducted: Comprehensive presale work was carried out, allowing Rostelecom.Restream to effectively present its competencies and solution. Customer Requirements were Analyzed in Detail: A deep understanding of Gazprom Neft's needs was ensured, which is critical for developing a relevant solution. A Competitive Solution was Proposed and Justified: A "Data Lake" solution was developed and presented, maximally addressing the oil and gas company's big data processing needs for finding new insights and profit growth opportunities. The Solution was Successfully Presented and Defended in a Tender: Demonstrating expertise and preparing compelling arguments contributed to winning the competitive selection. A Foundation for a Potential Implementation Project was Laid: The presale results created favorable conditions for securing a contract for the full-scale implementation of the Data Lake for Gazprom Neft.
16 | Telecom | SDS, Data Storage | Rostelecom.Restream | Enterprise Architect, Business Analyst | Project 'Storage' | RTK-SDS | Customer requirements were analysed, and a balanced solution for enterprise data storage (SDS - Software Defined Storage) was proposed, which allowed the organisation to make the right choice, enhance data reliability, availability, and processing speed, and save significant funds. | Rostelecom.Restream |  | 2016-11-01 | 2016-12-01 | Rostelecom.Restream operated in the field of data analysis for its parent company, Rostelecom. Data volumes were constantly growing, requiring reliable storage and accessibility. Various departments receiving diverse data (both structured and unstructured) had their own opinions on data storage and processing, which created a need for a unified and efficient solution. | I was tasked with selecting the optimal data storage solution for the enterprise. The task included analyzing requirements from various stakeholders, accounting for the diversity of data types and their lifecycles, and selecting and presenting solution options that could ensure data reliability, accessibility, and processing speed. | Requirements and Data Type Analysis: I analyzed the requirements received from stakeholders within our organization. Given that several departments received diverse data (both structured and unstructured) and each had its own opinion on data storage and processing, I categorized all data streams by type. Data Lifecycle Analysis: For each data type, I thoroughly analyzed its lifecycle, which helped determine optimal storage and access strategies. Formulated Solution Requirements and Constraints: I compiled a comprehensive list of requirements for the solution and imposed corresponding constraints, as well as requirements for the Software Defined Storage (SDS) system itself. Selection and Presentation of Solution Options: Subsequently, I was able to select several solution options that met all requirements and constraints and presented them to the architectural committee. Each option was accompanied by a description of its advantages and disadvantages. | As a result of my work: The Organization Received Balanced Solution Options: Well-thought-out and balanced solution options were presented, with described advantages and disadvantages. This helped Rostelecom.Restream make the right choice when selecting the storage system. Enhanced Data Reliability and Accessibility: Ultimately, this provided Rostelecom.Restream with additional benefits in service delivery: increased data storage reliability and availability. Increased Data Processing Speed: Data processing speed significantly increased, which is critical for analyzing large volumes of information. Customer Data Specificity Accounted For: The nature of each customer's data and its lifecycle were considered, leading to improved service quality and customer satisfaction. Significant Cost Savings: It is important to note that significant funds were saved because the solution was chosen correctly, and no unjustified expenses were incurred.
17 | Telecom | Enterprise Architecture, OCM | Rostelecom.Restream | Enterprise Architect | Enterprise Architecture | RTK-EA | Conducted EA Assessment. Delivered EA baseline and transformation roadmap. | Rostelecom.Restream |  | 2017-01-01 | 2019-01-01 | Rostelecom.Restream, as a subsidiary of the large operator Rostelecom, was actively developing and expanding. To ensure organic, reasonable, and manageable growth, strategic planning was required. The company's management expressed a need for a clear roadmap of proposed changes to guide this growth and future initiatives. | In my role as Enterprise Architect, the primary task was to create a roadmap for change. This necessitated conducting a comprehensive enterprise assessment, meticulously documenting its current state (baseline), gathering requirements for the future target state, and developing a detailed transformation plan. | Enterprise Assessment: Conducted a comprehensive assessment of the enterprise to gain a full understanding of its current business processes, organizational structure, information systems, and technological infrastructure. Stakeholder Interviews: Conducted numerous interviews with various stakeholders at all levels of the organization to gather their opinions, needs, and expectations for the future architecture. Current State Documentation (Baseline EA): Meticulously documented the current state of the enterprise architecture, creating a detailed "baseline" that served as a starting point for changes. For diagrams, I used Archimate notation, ensuring a standardized and understandable representation. Future State Requirements Gathering: Gathered and formalized requirements for the target (future) state of the enterprise architecture, considering the company's strategic growth and development goals. Transformation Roadmap Development: Based on the analysis of the current state and requirements for the future, and guided by the TOGAF methodology, I developed a detailed transformation roadmap. This roadmap included phases, projects, dependencies, and expected outcomes of the changes. Presentation and Alignment: Presented the developed roadmap, as well as the current and future state of the architecture, to management and key stakeholders for discussion and alignment. | A Carefully Developed Change Roadmap was Produced: The company's management received a clear, comprehensive, and meticulously developed roadmap for future transformations. Current and Future EA States Presented: Detailed descriptions of the current baseline enterprise architecture (EA baseline) and its target state were created and presented, ensuring a unified vision. Foundation Laid for Organizational Decision-Making: The results of my work served as a solid foundation for making important strategic and organizational decisions regarding the company's development. Basis for Change Implementation Ensured: The roadmap and state descriptions provided a clear plan for the subsequent implementation of changes, contributing to Rostelecom.Restream's organic and managed growth.
18 | Telecom | Data Analytics, Digital Marketing | Rostelecom | Business Architect | Data Lab | RTK-DL | A new subdivision was created to handle data for the marketing department. The data includes consumer behavior. Tools for behavior analysis, segmentation, omnichannel communication, and a recommendation system were created. | Rostelecom | Hadoop, Data Lake | 2017-02-01 | 2019-02-01 | Restream, a subsidiary of Rostelecom—a major provider of wired and wireless internet and communication services—faced the need to analyze vast amounts of data from clients, such as visited websites, user interests, and web behavior. The goal was to more accurately target advertisements, react to user churn in a timely manner, and gain other marketing advantages. | In my role as a Business Analyst and later as an Enterprise Architect, I was tasked with developing the concept for a new data analysis subdivision. The task included: designing the concept for its operation, defining the necessary tools, technologies, and processes for this department, and establishing its goals, objectives, and methods for evaluating its results. | Developed Subdivision Concept: I designed a detailed concept for the new subdivision, including its goals, tasks, organizational structure, and functions. Presented Solution to Stakeholders: I presented the subdivision's goals, tasks, necessary tools, and technologies (Hadoop, Data Lake) to the architectural committee and key stakeholders. Developed Tools and Processes: I developed concepts for tools for behavior analysis, segmentation, omnichannel communication, and a recommendation system. Developed Metrics and Evaluation Methods: I established methods for evaluating the quality and success of this subdivision's work, as well as a list of expected outcomes. Collaborated with Teams: I worked to ensure that data that was previously deemed unnecessary could be used effectively. | A New Subdivision was Created: Based on my proposal, Rostelecom created a new subdivision consisting of analysts, project managers, and technical specialists. Previously Untapped Data Utilized: The company successfully began analyzing data that was previously left unused and now uses it for business purposes. Foundation for New Profitable Products: The work of this subdivision provided the foundation for launching a whole range of new, profitable company products, such as targeted advertising, a recommendation system, a churn reaction system, traffic filtering, redirects, and much more. Enhanced Marketing Effectiveness: The company's marketing capabilities expanded significantly, allowing for more precise audience targeting.
19 | Telecom | Data Analytics, Data Management | Rostelecom | Enterprise Architect | DWH Audit (EKHD) | RTK-EKHD | A comprehensive analysis of the implementation of the Unified Corporate Data Storage System was conducted, and recommendations for its improvement were provided. | Rostelecom |  | 2018-03-01 | 2018-12-01 | Rostelecom had implemented the Unified Corporate Data Storage System (EKHD). After implementation and launch, the system's shortcomings became clearly visible: confusion in data sources, incorrect data processing, a lack of order in storage, non-compliance with data delivery SLAs, and other issues that impacted the business and raised questions about the effectiveness of the investment. | My task as an Enterprise Architect was to audit the system itself, the surrounding enterprise landscape, interview stakeholders, and interview the system's creators, including subcontractors. I needed to understand why the system was not working as intended and how to fix it. | Conducted Interviews: I held a series of interviews with stakeholders, developers, and subcontractors to gather information about the system's operation. Architectural Analysis: I created an architectural diagram and system model, linking all the problems I had identified to it. Developed an Improvement Plan: I developed a plan of fixes and improvements that could be undertaken to rectify the situation. Comprehensive Recommendations: The plan included both technical changes related to storage technologies and organizational changes related to a review and reorganization of data acquisition processes, data management, and data lifecycle management. | The Project Was Salvaged: The company was given the opportunity to correct a costly project, which then began to provide value. Data Storage Costs Reduced: Data storage costs were reduced by 15%. Improved Data Management: There was more order in data management. Report Preparation Time Reduced: The time to prepare reports for management purposes was reduced by 4-5 times. Foundation for Decision-Making: The system became the basis for management decisions for marketing operations. Numerous Indirect Effects: Many indirect effects were achieved, such as a reduction in accounts receivable, savings in time and labor on client and partner notifications, and more.
20 | Telecom | Data Analytics, Digital Marketing | Rostelecom | Business Analyst | B2B Mailing Automation | RTK-B2B | Architecture for a multi-channel communication system for B2B interaction was developed. Documentation was handed over for implementation, which led to increased additional sales and customer satisfaction. | Rostelecom |  | 2017-04-01 | 2019-04-01 | Rostelecom had problems with communications with client organizations. There was no system that allowed for mailings to a specific segment of business consumers. It was assumed that creating such a system would enable targeted mailings and increase sales opportunities to existing clients. | In my role as Solution Architect and Business Analyst, my task was to conduct a survey, understand the current situation, take into account the opinions of stakeholders, and design a system that could solve the described problems. | Conducted Interviews: I conducted interviews with numerous interested parties from different departments to gather existing information and identify needs. Identified and Formalized Rules: I identified and formalized the rules for how to segment message recipients, how to obtain information for mailings, how to approve it, and how to send it to clients. Created a Solution Architecture: Following this, I developed a solution architecture for a multi-channel communication system capable of implementing these rules. Prepared Documentation and Handed Over for Development: I prepared complete documentation on the system requirements and handed it over for development. | A Clear Action Plan was Received: The company received a clear action plan to solve the existing problem. Reduced Implementation Costs: The clear and understandable description reduced the costs of implementing the solution. Increased Additional Sales: After implementation, the company gained the ability to target mailings to groups of consumers and thus increased additional sales. Increased Customer Satisfaction: The improvement in the quality of communications and targeted mailings led to an increase in customer satisfaction.
21 | Telecom | Account Management | Rostelecom | Solution Architect | Informing clients about the debt on their account (SPDZ) | RTK-SPDZ | A unified approach for managing client notifications was proposed. A solution architecture was created, and documentation was handed over for implementation, which significantly reduced accounts receivable (by three times) and brought significant economic benefits. | Rostelecom |  | 2017-05-01 | 2019-05-01 | The company's growing accounts receivable reduced its effectiveness and prevented the use of funds in operational activities. The tool for informing clients was outdated, relying on reconciliation statements and email correspondence, which proved inefficient and labor-intensive. | My task was to create a system that would solve these problems. To achieve this, regular and accurate notifications were introduced to debtors, with the expectation of significantly reducing accounts receivable. | Requirements Gathering: I met with stakeholders and gathered their requirements and constraints for the system. Solution Design: Based on the gathered information, I designed the solution architecture for the accounts receivable notification system (SPDZ). Documentation Preparation: The documentation for the solution was prepared and handed over for development. | A Debtor Notification System was implemented: The company implemented the system designed based on my specifications. Significant Reduction in Accounts Receivable: Client accounts receivable were significantly reduced by a factor of three. Indirect Effects were Gained: The time for reconciling mutual settlements with clients was reduced, as was the volume of paper documentation processing and email correspondence. A Significant Economic Result was Achieved: Overall, the system provided a significant economic result for my company.
22 | Telecom | Inter-operator Communication | Rostelecom | Solution Architect | O2O Interaction | RTK-O2O | A concept for interaction architecture between operators was developed. A solution was created. As an alternative, a solution for inter-operator settlement registration based on blockchain was proposed. | Rostelecom |  | 2017-06-01 | 2019-06-01 | Rostelecom had very complex relationships with other operators, with companies supplying each other services through intricate schemes that included multilateral offsetting of debts. This led to difficulties with settlement reconciliation, the speed of this reconciliation, and an abundance of paperwork. | Management tasked me with simplifying the accounting of mutual settlements, accelerating reconciliation, and reducing the number of errors during reconciliation. The goal was to free up additional funds for operational activities and increase the company's overall efficiency. | Analyzed Partner Interactions: I held numerous meetings with company stakeholders and partners to understand the complex interaction and settlement scheme. Designed a Target System: I designed a target system capable of simplifying accounting, accelerating reconciliation, and reducing errors. Aligned the Solution: I held meetings to align the designed solution with all interested parties. Prepared Documentation: The documentation was handed over for development. Developed an Alternative Blockchain Solution: As an additional exercise, I developed a solution variant using blockchain technology, created a POC (Proof of Concept), and demonstrated the advantages of such a solution. | A Clear Action Plan: The company received a clear action plan to solve the problem, as well as an agreed-upon solution that could be launched. Potential Savings: The potential savings from implementation amounted to thousands of man-hours per year, and the reduction in errors could save the company millions of dollars per year. Increased Efficiency: The simplification of accounting, acceleration of reconciliation, and reduction of errors significantly increased the company's overall efficiency.
23 | Telecom | Data Management, Digital Marketing | Rostelecom | Enterprise Architect, Solution Architect | Data Management Platform (DMP) | RTK-DMP | Architecture for a DMP was created and a business-driving implementation was proposed, which allowed the company to launch several new profitable businesses and get a foundation for building a business for years to come. | Rostelecom | Big Data, Hadoop | 2017-07-01 | 2019-07-01 | Rostelecom, the largest provider of communication services in Russia, offering wired and mobile telephony, cable and wireless internet, receives a massive amount of valuable data from providing these services. This data had huge potential for creating new services and increasing profit. | It was decided to analyze this data and provide a suite of services based on it for both internal and external clients. For this, the Data Lab team (Project #18) was created, and to support the Data Lab's work, a corresponding infrastructure (both hardware and software) was needed to effectively process and store this data. | Stakeholder Interaction:I conducted a series of meetings with stakeholders from the Data Lab team who were going to work with the data, as well as with data suppliers and consumers. Requirements Gathering:I gathered their requirements, along with integration, functional, and non-functional requirements. Architectural Documentation:I created an architectural document that outlines the future solution, beginning with the concept, progressing to the business architecture, and concluding with the information and data layer. The document described the logic for building the Data Management Platform (DMP). Recommendations:I proposed and justified the architecture of the solution and its implementation. | Foundation for Implementation was Created:The architectural document was handed over for implementation, and the organization began the project to implement the system. New Businesses Launched:The system had the potential to launch several new profitable businesses for the company, such as segmentation for targeted advertising, contextual advertising, event-based advertising, a recommendation system for online stores, and its own streaming service, and many others. Long-term Strategy:This gave the company a clear roadmap and a foundation for building a profitable business for years to come.
24 | Telecom | Digital Marketing | Rostelecom | Enterprise Architect | Loyalty Program Effectiveness Evaluation | RTK-PLE | A comprehensive approach and methodology were developed for evaluating the effectiveness of loyalty programs. Practical changes were made at the IT systems level to implement the evaluation process, which led to an increase in revenue and profit through additional sales and new marketing initiatives. | Rostelecom | The work utilized technologies such as Radius, IoT, Data Management, and DWH for data collection and processing. | 2018-08-01 | 2018-12-01 | Rostelecom, as the largest telecom operator, had a loyalty program, but it was very basic and used inefficiently. Customers simply accumulated points that they could spend on communication services. The customer journey was very primitive, lacking segmentation, offer targeting, analytics, and other modern technologies, which diminished the program's potential as a business tool. | My task was to audit the loyalty program from both a business and a systemic, architectural perspective. I needed to find growth opportunities for the loyalty program so that it could become an effective tool for increasing profit. | Conducted Audits and Interviews: I conducted surveys and interviews with both business and technology teams to understand the internal workings of the loyalty program and identify its weaknesses. Analyzed Experience and Wishes: I took into account the business's wishes and used my experience with loyalty programs for Gazprom Neft (projects #6 and #12) to find the best solutions. Developed an Effectiveness Evaluation Methodology: I developed and presented a methodology for evaluating the loyalty program's effectiveness, which included specific metrics and indicators. Implemented Changes at the IT Systems Level: I proposed and supervised practical changes at the IT systems level necessary to implement the loyalty program effectiveness evaluation process. Technologies: The work utilized technologies such as Radius, IoT, Data Management, and DWH for data collection and processing. | Inefficiency Discovered and Eliminated: The inefficiency of the loyalty program was timely discovered, clearly demonstrated to stakeholders, and successfully eliminated. Increased Revenue and Profit: The company as a whole increased revenue and profit through additional sales to customers. Implemented New Tools: A recommendation system, additional promotions, and marketing events were implemented.
25 | Transport | Strategic Management, Strategic Planning, Enterprise Architecture | DME Airport | Enterprise Architect | Enterprise Strategy Development and Risk Management | DME-25 | Increased the airport's resilience to potential threats. Provided valuable information for informed strategic decisions. Strategic directions are defined, and strategic initiatives to be undertaken in the next period are described. | DME Airport |  | 2019-11-30 | 2021-02-15 | In 2019, I joined the Strategic Group at Domodedovo Airport as Chief Architect. The enterprise annually develops a strategy to define its development directions, and it also faces the need to assess and manage potential risks in the dynamic aviation industry. | Strategic: Participate in the annual enterprise strategy development process (from August until the strategy defence before the strategy committee), focusing on topics relevant to my experience: market situation, technologies, information management, and information technology. Strategic: Conduct risk assessment for the airport, develop response plans, analyze trends, and forecast their impact on future operations. Operational: Analyze past analytical reports and prepare new ones on various topics. | Strategic: I actively participated in strategic sessions and analytical work, formulating proposals for specific areas and integrating them into the overall enterprise strategy. I conducted a comprehensive risk assessment, identifying potential threats to airport operations and development, and developed detailed response plans for them. I conducted trend analysis in the aviation industry and related fields, as well as forecasting their impact on the airport's future operations. Operational: Collected data and conducted research. Systematically analysed analytical reports from previous years to identify patterns and prepare new analytical reports on current topics. | Strategic: Made a significant contribution to the formation of the annual enterprise strategy, ensuring that key aspects of the market situation, technological development, and effective information and IT management were considered. Strategic: My work on risk assessment and response plan development increased the airport's resilience to potential threats. Strategic: The preparation of analytical reports and trend forecasting provided management with valuable information for informed strategic decisions.
26 | Transport | Strategic Management, Strategic Planning, Enterprise Architecture | DME Airport | Enterprise Architect | Crisis Transformation of DI IT Department | DME-26 | Successfully reoriented the IT department's work towards external clients. Opened new revenue streams and ensured enterprise sustainability during the crisis. | DME Airport | not applicable | 2019-03-30 | 2019-12-31 | With the onset of the COVID-19 pandemic, the Chairman of the Board of Directors tasked me with leading crisis management in the Domodedovo Integration (DI) IT department, which traditionally served only the internal client – the airport. | Strategic: Develop and implement measures to preserve the enterprise during the crisis, reorienting the IT department's work towards external clients to ensure sustainability and find new revenue streams. Operational: Identify and repackage enterprise products for the external market, develop a market entry strategy, and a marketing plan. | Strategic: In collaboration with DI's marketing department, I developed and implemented strategies to adapt the business model, focusing on providing IT services to external clients. A market entry strategy for new services was developed. Operational: We identified enterprise products that could be offered to external clients, and based on them, created a product line oriented towards the external market. A review of existing products was conducted, many of which required repackaging and updating to meet market requirements. A marketing plan was developed to promote the introduction of new services. | Strategic: Successfully reoriented the IT department's operations, ensuring its sustainability during the crisis and opening new revenue streams through effective product launch into the external market. Operational: Received a letter of commendation from management for my contribution to the adaptation and preservation of the enterprise.
27 | Transport | Enterprise Architecture, Product Management, OCM | DME Airport | Enterprise Architect | Product Portfolio Harmonization and Product Development Process Reengineering | DME-27 | The product portfolio was reduced from 4,600 to 1,200 products without compromising profitability. Time-to-Market (TTM) reduced by 3 times. "Profit-per-Product" indicator significantly increased. | DME Airport | MS SQL, Power BI | 2019-11-30 | 2021-02-15 | The product portfolio of Moscow Domodedovo Airport was highly inefficient: 4600 products without detailed classification, with duplication, functional overlap, and outdated positions. There was no product strategy or roadmap, and the product management and regulatory systems were outdated. | Strategic: Maximize the "profit-per-product" indicator and enhance the overall efficiency of the product portfolio by creating a structured approach to product development and management. Operational: Harmonize the portfolio, eliminate inefficiencies, and update product management and regulatory systems. | Strategic: Conducted a comprehensive analysis of the existing product portfolio. Developed a detailed classification system. Created a robust product strategy and developed roadmaps. Implemented advanced analytics to support data-driven decision-making. Operational: Eliminated duplication and functional overlap. Updated and modernized product management and regulatory systems. Created training materials and a methodology for product managers to work by in each of the 19 legal entities of the airport. | As a result of my work: Successful Reorientation: The IT department's operations were successfully reoriented, ensuring its sustainability during the crisis and opening new revenue streams through the effective launch of products into the external market. Formal Recognition: I received a letter of commendation from management for my contribution to the adaptation and preservation of the enterprise.
28 | Transport | Strategic Management, Strategic Planning, Enterprise Architecture | DME Airport | Enterprise Architect | Enterprise IT Strategy Development and Alignment | DME-28 | A cohesive IT strategy was created, integrated with business goals. Enterprise architecture was developed, and key vendors/solutions were selected. | DME Airport | not applicable | 2021-02-04 | 2021-08-04 | The problem was a lack of a cohesive IT strategy that effectively supports the airport's future growth. With a strong IT background, I was involved in developing the airport's IT strategy. At this stage, I already held the position of Head of IT Strategy. | Strategic: Ensure the projection of strategic IT initiatives, discussed at the highest level within the corporate strategy, into specific IT department strategies (DI), so that DI's IT strategy and activities precisely align with the ideas and initiatives envisioned at the overall enterprise level. Strategic: Create a cohesive IT strategy that would effectively support the airport's overall business goals. | Strategic: I worked on aligning high-level enterprise IT goals with the operational plans and strategies of individual IT departments, ensuring their close interconnectedness and mutual support. I was responsible for developing the enterprise architecture. I conducted negotiations with key vendors (such as SITA, Amadeus, Fujitsu, Wincor Nixdorf, and others). I performed vendor comparisons and selections, as well as solution comparisons and selections, to ensure alignment with strategic goals. | Strategic: Contributed to the creation of a cohesive IT strategy that effectively supported the airport's overall business goals, ensuring strategic alignment across different levels of IT management. The developed enterprise architecture, along with the selected vendors/solutions, laid the foundation for future technological transformations.
29 | Transport | Strategic Management, Strategic Planning, Enterprise Architecture | DME Airport | Enterprise Architect | Comprehensive Reorganization of DI IT Department and Implementation of Modern Practices | DME-29 | The IT subsidiary (DI) gained the ability to work with external clients. New methodologies for change management (TOGAF) and software development (Agile) were implemented. The foundation was laid for improving the department's image and increasing profitability. | DME Airport | not applicable | 2021-02-04 | 2021-08-04 | The Domodedovo Integration (DI) IT department suffered from outdated working methods and technologies, leading to low efficiency and unprofitability. The department's image among IT specialists was low, making it difficult to attract talented personnel, as they sought modern working conditions, flexible methodologies (e.g., Agile), and an innovative environment. This resulted in a severe talent shortage and the use of outdated technologies. | Strategic: Create a corporate IT strategy fully aligned with the airport's business goals, and conduct a reorganization of the IT department to enhance its efficiency and adaptability, improve its image to attract talent, and ensure profitability, as well as implement a modern methodology for change management and software development. Operational: Assess the current IT landscape, organize workshops, map IT capabilities to business needs, and propose an IT development roadmap. | Strategic: Conducted an assessment of the current IT landscape. Mapped IT capabilities to business needs. Proposed an IT development roadmap. Developed the IT strategy based on the TOGAF methodology and implemented Agile principles into the department's work. Actively participated in the reorganization process of the IT department, optimizing its structure and processes, and implementing modern approaches to management and development. Operational: Organized and conducted workshops with key stakeholders. | Strategic: The airport received a clear, actionable IT strategy integrated with the overall business strategy. A TOGAF-based IT strategy was successfully developed, and Agile was implemented, significantly enhancing the strategic value and operational efficiency of the IT department. The IT subsidiary (DI) gained the ability to work with external clients, opening new revenue streams. Through reorganization and the implementation of modern practices, the foundation was laid for improving the department's image, attracting qualified IT specialists, and increasing profitability. The company adopted a new, modern methodology for working with changes, based on TOGAF, and a software development methodology based on Agile. Operational: Training and methodological materials were prepared, and training sessions were conducted with personnel for a quick start to development using the Scrum methodology.
30 | IT Services | HR, Data Management, Workflow Management | EPAM | Lead Business Analyst, Enterprise Architect | Human Resource Management System (HRMS) | EPM-HRMS | Requirements were gathered and technical specifications for an HR system were prepared, which led to improved efficiency, significant time savings, and compliance with data privacy regulations. | EPAM | Java | 2021-08-11 | 2022-05-31 | EPAM Systems had a need to improve its internal human resources management system. The company was undergoing significant organizational changes related to the majority of employees transitioning to remote work and numerous relocations. It was also necessary to perform data migration from older accounting systems to a new one. | In this project, I needed to handle the part related to the accounting of people's profiles (not only employees but also external students, internal students, potential employees, contacts at various events, community members, and so on). I had to create requirements for storing such profiles and for their dynamic transformation. The complexity was also in the fact that the company's branches are located in many countries (58 countries), and it was necessary to take into account the legislation on working with personal data. | I undertook the following actions over a period of 10 months (from August 2021 to May 2022): Conducted Interviews: I held many meetings with stakeholders and formalized the organization's processes in their current state. Identified Requirements: I identified the requirements for future processes and created a plan for their transformation. Formulated System Requirements: I prepared the requirements for the changes and handed them over for implementation. | As a result of my work: Improved the People Accounting System: The company was able to improve its system for accounting for people (not just employees), which increased the efficiency of various services, including marketing, the learning portal, HR, and others. Time Savings and Error Reduction: The proposed changes saved hundreds of hours of labor per month and reduced the number of accounting errors, which increased client and employee satisfaction and reduced the company's reputational risks. Compliance with Legislation: Compliance with personal data processing legislation in the various countries where the company operates was ensured.
31 | IT Services | Data Management | EPAM | Enterprise Architect | Single Profile Concept | EPM-SPC | A single profile concept was created and used as a foundation for four new projects, leading to significant time savings, process unification, and improved company image. | EPAM |  | 2022-01-01 | 2022-07-31 | EPAM Systems had multiple fragmented systems for processing data about employees and various contacts (e.g., student interns, community members). These discrepancies in contact accounting became significant and created confusion and problems in business processes, hindering data unification and effective management. | Management tasked me with creating a single profile concept for accounting for all types of contacts. This profile was to be used not only for employees but also for other contact types. It was necessary to analyze existing accounting processes and develop rules for transforming these profiles, so that this concept could then be extended across the entire organization. | Analysis of Current Processes: I conducted numerous interviews with stakeholders to gain insight into how existing accounting processes functioned across various systems. Formalization and Design: I formalized the existing processes and developed a description of the future information architecture. I created the single contact profile concept, detailing its business architecture (management processes) and information architecture (information concept, data flows). | A Single Profile Concept was Created: I created a single contact profile concept that became the foundation for the future development of information systems. Launched New Projects: The results of this project led to the launch of four new projects in the organization (e.g., Central Permission Engine — project #32, Profile Storage — project #33). Significant Savings and Unification: These projects laid a solid foundation for further information system development, streamlining processes across the organization and resulting in substantial savings in work hours. Improved Company Image: The improvements in data and process management had a positive impact on the company's image.
32 | IT Services | AAA | EPAM | Enterprise Architect | Central Permission Engine (CPE) | EPM-PSR | A concept for a centralized permission model was formulated, allowing for access rights to be assigned based on both role-based and resource-based models. | EPAM |  | 2022-03-29 | 2022-10-22 | The company had numerous systems for internal and external use. Both company employees and external participants—such as students and subcontractors—could use the systems. Furthermore, the information used by the company also required access restrictions. In the current state, access management was decentralized and handled separately in each system and each business process. | To clearly restrict access to company resources, both information resources and IT systems, a single permission management system was required. This was expected to reduce the labor costs of managing access to systems and information. | Information Gathering and Analysis: I collected information about interested parties and their wishes, as well as the current state of processes and systems. Target System Design: Together with the solution architect, I developed the target state of the system. Requirements Formalization: I formalized the requirements and handed them over for development. | A Single Permission Management Engine was Created: The company received a single permission management engine with flexible configuration options. Flexible Configuration: Permissions could be granted based on a role-based or resource-based model, and business and technical rules for permission management could be set. Potential Savings and Risk Reduction: This system has the potential to save the organization millions of dollars annually and eliminate the risks of unauthorized access to information, thereby improving the company's image as a reliable partner.
33 | IT Services | HR, Data Management, Workflow Management | EPAM | Lead Business Analyst | Unified Profile Storage | EPM-PSR | Client profile architecture was developed, profile storage prepared, and data migration successfully completed, accounting for dynamic system changes and format transformations, leading to active integration by consuming systems. | EPAM |  | 2022-03-29 | 2022-10-22 | Following the completion of my previous project (Project #28), which established the Unified Client Profile Concept, there was a critical need to practically implement this concept. The company required specialized profile storage capable of consolidating data from various sources and providing centralized access to unified client information. | My task, as an Enterprise Architect, was to create the client profile storage, which included developing its architecture, migrating data from existing systems, and establishing clear rules for its operation and interaction. The project demanded meticulous work on data architecture, accounting for dynamic changes in source systems, and transforming various data formats. | During the project, which ran from March to October 2022, I took the following actions: Team Assembly and Organization: As a Lead Business Analyst, I assembled and organized the work of the analyst team, fostering effective collaboration to achieve project goals. Requirements Gathering and Conceptualization: We conducted comprehensive requirements gathering for the profile storage, engaging with various stakeholders. Based on the insights gained, a detailed concept for the storage was developed. Rule and Data Architecture Development: Significant attention was given to establishing operational rules for the storage, creating an optimal data architecture, and defining requirements for the data migration process. This involved addressing dynamic changes in source systems and transforming diverse data formats. Migration Preparation: Plans and procedures for data migration were developed and agreed upon, ensuring the integrity and quality of the transferred information. | As a result of our work: A Centralized Data Storage was Created: The company gained a functional and scalable client profile storage. Active Integration by Consuming Systems Began: Various consuming systems started connecting to the new profile storage, confirming its demand and central role in the company's data ecosystem. A Foundation for Future Growth was Established: The project laid a strong foundation for the continued development and expansion of the storage's functionality, as more systems continue to connect, indicating its success and adaptability.
34 | Retail | Digital Transformation | EPAM | Enterprise Architect | Retail Digital Transformation | DELB-CRP | A strategic roadmap for the core retail platform was developed, enabling the client to make informed decisions, optimize investments by avoiding functional duplication, and leverage underutilized technologies for further business impact. | Ahold Delhaize |  | 2022-12-05 | 2023-02-28 | The Customer, a retail company that had undergone significant mergers and acquisitions, was facing a complex and inefficient IT landscape. To support its growth goals through online and offline channels, the company needed a clear plan to integrate its various retail solutions into a single strategy across the European region. The goal was to leverage underutilized technologies to add value for its brands and customers. | My task was to develop a strategic roadmap for an integrated core retail platform that aligned with the customer's role as a technology enabler, driving omnichannel growth and operational excellence. This roadmap needed to outline a 1–3-year development horizon and include a capability assessment to increase maturity. | Comprehensive Discovery Scan: Conducted a comprehensive discovery scan of the entire enterprise's business and application landscape to identify current capabilities and gaps. Capability Analysis: Performed a detailed capability analysis, optimization, and planning. Application-Capability Mapping: Mapped application functions onto enterprise capabilities to ensure alignment with business goals. Stakeholder Collaboration: Collaborated with key stakeholders to define and refine the strategic roadmap. Report Delivery: Delivered a detailed discovery report with a comprehensive overview of the current enterprise landscape, which simplified management decision-making. Roadmap Development: Developed a detailed strategic roadmap for developing the core retail platform. | Clear and Comprehensive Overview: The customer was provided with a clear and comprehensive overview of the current enterprise landscape, simplifying management decision-making. Detailed Strategic Roadmap: A detailed strategic roadmap for developing the core retail platform was delivered, ensuring alignment with the customer's business objectives and technological advancements. Value-Added Technologies: The work enabled the customer to leverage underutilized technologies, driving further impact and value for their brands and customers. Informed Decisions: The clear and structured strategic plan enabled the client to make informed decisions on platform development and transformation. Investment Optimization: The roadmap helped the company avoid functional duplication and optimize IT investments.
35 | Telecom | Digital Transformation, Business Transformation | EPAM | Enterprise Architect | Digital Business Transformation | BTCL-ARCO (1) | BTC prepared its business transformation from a traditional telecom to a digital service marketplace. A target-state information architecture was developed as a foundation for future changes, providing the client with a clear plan for system and information transformation. | BTC |  | 2023-05-15 | 2023-09-15 | BTC, a telecom company, was undergoing a digital transformation to evolve from a traditional mobile operator into a digital service marketplace. Competitive pressure intensified the urgency to adapt, as rivals had already started offering digital services beyond core telecom offerings. BTC was expanding into new digital industries (eHealth, FinTech, Cloud) and needed a minimal viable architecture (MVA) and information architecture vision. | As an Enterprise Architect, I was tasked with analyzing the current state of the company's information architecture and designing a target-state model that would support the new business strategy. Analyse the current state and define target information architecture and roadmap. | Conducted landscape assessment, designed target information architecture, created customer journeys, capability maps, and proposed a change roadmap. I studied how the client's business was structured, then organized and streamlined their key information entities. I developed a target-state information model — the Information Architecture — showing how data entities would be structured and related in the future state of the business. | The client received a clear plan for transforming the information architecture to support new business directions. The client received a comprehensive Information Architecture for the enterprise’s future state. This clarified how their business would function, what information entities would be involved, and how they would interact — paving the way for system and data-level transformation.
36 | Manufacturing | AAA | EPAM | Solution Architect | Autorisation Cockpit | DANF-ACO | A clear implementation roadmap and a capability map were developed, enabling the client to select the right vendor and launch development with a clear, cost-effective plan that met business needs. | Danfoss |  | 2023-10-23 | 2024-02-23 | The client, International manufacturing company, a leading company in the Manufacturing & Auto industry, needed to develop a new web application called Authorization Cockpit. This application was a new CIAM (Customer Identity and Access Management) solution that would manage user and partner authorizations. The application had to be built from scratch, and the client needed to get the MVP (Minimum Viable Product) live in the second half of the year. | My task was to define, design, and develop the Authorization Cockpit web application. This involved ensuring it aligned with the client's requirements, leveraging their UI components library, creating a prioritized backlog of development tasks, an implementation roadmap, and a capability map for the enterprise. The goal was to provide a prioritised, cost-efficient plan and a vendor choice. | Comprehensive Landscape Scan: I conducted a comprehensive scan of the enterprise landscape, including its business, applications, and architecture. Requirements Collection: I conducted interviews and collected requirements, business rules, and restrictions for the future solution from various stakeholders. Requirements Processing: I processed the business requirements and formulated functional requirements. Solution Development Participation: I actively participated in the development of the solution. Prioritized Backlog & Roadmap: I prepared a prioritized backlog of development tasks and an implementation roadmap. Capability Mapping: I developed a capability map for the enterprise in its current and future states. Vendor Information Preparation: I prepared documentation for vendor selection to help the client choose the right supplier. | Streamlined and Prioritized Requirements: The existing requirements were streamlined and prioritized, which enabled the customer to select the right supplier and move forward with development at the lowest cost. Aligned Solution: The chosen solution closely met the customer's business needs, providing a clear path for development and implementation. Well-Defined Roadmap and Capability Map: A well-defined implementation roadmap and capability map were delivered, facilitating effective management and decision-making.
37 | Manufacturing | Digital Transformation, Business Transformation | EPAM | Enterprise Architect | Business Transformation | DANF-L2C | A comprehensive solution blueprint and capability map were delivered, providing the client with a clear roadmap for implementing a subscription management solution that aligns with business objectives and technological capabilities. | Danfoss |  | 2024-03-13 | 2024-06-07 | Our client, a major manufacturing company, made the strategic decision to transition from a pure equipment manufacturing business to a service-based business. They needed to design a subscription management solution that would connect the order-to-quote flow, acting as an intermediary between CRM and ERP systems. This required a thorough analysis and design phase to ensure the solution met business needs and integrated seamlessly with existing systems. | In my role as an Enterprise Architect, I conducted an analysis and design stage to define and blueprint a subscription management solution. I needed to gather requirements, develop a comprehensive blueprint, and create a prioritized implementation roadmap. | Landscape Survey: I surveyed the enterprise landscape to gather requirements, business rules, and constraints for the future solution. Stakeholder Engagement: I conducted interviews and workshops with stakeholders to understand their needs and expectations. Capability Mapping: I developed an enterprise's capability map in both its current and future states. Full-Scale Blueprint: I prepared a full-scale blueprint for the future state of the subscription solution. Prioritized Roadmap: I created a prioritized backlog and roadmap for implementing the solution. Vendor Selection Framework: I developed a detailed framework for selecting a solution provider. Development Participation: I actively participated in the development of the solution. | Streamlined and Prioritized Requirements: I organized and prioritized the solution requirements, enabling the selection of the right supplier and facilitating the transition to the development stage. Clear and Comprehensive Roadmap: We provided the client with a clear and comprehensive roadmap for implementing the subscription management solution, ensuring alignment with business objectives and technological capabilities. Actionable Blueprint and Capability Map: A full-scale blueprint and capability map were delivered that guided the development process and supported effective decision-making.
38 | Telecom | Product Management | EPAM | Product Domain Architect | Product Domain Transformation | BTC-ARCO (2) | Reorganized product domain, created plan, initiated vendor selection | BTC |  | 2024-09-02 | 2025-03-25 | BTC continued its transformation into a digital services marketplace and needed to rework the product domain architecture to support partner products, bundling, and better product management. | Develop a concept and roadmap for the product domain aligned with business strategy and other domains. | Analysed product domain maturity and pain points, created a domain concept, designed a capability model and target architecture, developed a change plan, coordinated with other domains, and launched vendor selection for Catalogue and Marketplace solutions. | Delivered an actionable domain development roadmap and initiated procurement processes for key solutions.
39 | Oil & Gas | Loyalty Program | EPAM | Enterprise Architect | Architecture Analysis for Fuel Retail | ADNO-BCP | Проведено обследование ландшафта заказчика. Resolved loyalty issues, gave future IT landscape improvement plan | ADNOC |  | 2024-11-01 | 2025-01-31 | ADNOC experienced retail outages due to failures in the loyalty programme, affecting fuel sales and damaging reputation. | Investigate the cause of failures and propose long-term improvements. | Analysed a complex landscape (loyalty, retail, fuel systems, POS), identified weak points, held stakeholder interviews, and developed recommendations for system improvement and resilience. | Provided a clear root-cause analysis and strategic recommendations, enabling the client to restore operations and plan future IT improvements.
40 | Finance | Blockchain, Finance, Payments | EPAM | Enterprise Architect | Private Blockchain POC – National Stablecoin | EPM-AST | A solution designed to meet requirements and constraints, along with a roadmap for future changes, was delivered to the Client, leading to the start of the implementation project. | Bank, Integrator |  | 2025-02-20 | 2025-06-30 | This project was a Proof of Concept (POC) for a leading bank in Asia. The bank faced the need to establish proof of concept for a national stablecoin currency based on a private blockchain. This required rapid validation of the idea and demonstration of technical feasibility. | In my role as an Enterprise Architect, the key task was to gather requirements for a private blockchain system for a national stablecoin, create a solution concept, and provide the Client with a clear roadmap for the next steps towards implementation. | To achieve these goals, I undertook the following actions during the project (from 01- 2025 to 06-2025): Requirements Gathering: I actively collaborated with stakeholders from the bank and the integrator to collect and clarify all functional and non-functional requirements for the private blockchain system and the national stablecoin. Solution Concept Development: Based on the gathered requirements, I prepared a detailed solution concept, outlining the architecture, key components, and operating principles of the private blockchain, as well as the mechanisms for issuing and circulating the stablecoin. This concept was agreed upon with the Client. Activity Prioritization and Roadmap Creation: I conducted activities to prioritize subsequent actions, defining key stages and tasks for full-scale implementation. Based on this, a clear roadmap was developed, indicating where and how to proceed. | As a result of my work: Client Received Developed Solution: The bank was provided with a detailed and agreed-upon solution, taking into account all identified requirements and constraints for the private blockchain and stablecoin POC. Roadmap for Future Changes Provided: The client received a clear roadmap for subsequent implementation phases, which provided strategic vision for the project. Implementation Project Started: The successful completion of the POC and the provision of the roadmap led to the initiation of the full-scale implementation project, confirming the value of the proposed solution.
41 | Oil & Gas | C&B, HR | EPAM | Enterprise Architect | Oil & Gas Company | ADNO-TRMS | The organization received a ready-to-implement target process description and AI agent requirements, prepared for the deployment of a new AI-automated process. | ADNOC |  | 2025-06-09 | 2025-07-18 | Client: A vertically integrated oil and gas company Employer: EPAM Systems The client aimed to significantly overhaul and optimize their existing process for planning and calculating fixed and variable remunerations. The current process was likely inefficient, time-consuming, prone to errors, and carried human-factor risks, including potential for corruption in bonus and incentive payouts. | As a Lead Business Analyst, my primary task was to redesign the remuneration planning and calculation process, transforming it into an optimized, target-state model. A critical aspect of this task was to identify and design specific process segments that could be enhanced or automated using Artificial Intelligence (AI) technologies. My role also encompassed organizing team efforts, selecting the appropriate methodology, facilitating all necessary workshops, and producing all required project documentation. | To achieve these objectives, I took the following actions: Research and Best Practices Integration: I thoroughly researched industry best practices and recommendations from leading consulting agencies regarding remuneration processes. I also leveraged insights from EPAM's past projects and expert advice to inform the solution design. Stakeholder Engagement and Requirements Gathering: I organized and led a series of meetings with approximately 10 key stakeholders from various departments across the client organization. This ensured a deep understanding of their current process challenges, pain points, and expectations for the future system. Solution Concept Development: Based on the analysis of best practices and stakeholder input, I developed a comprehensive conceptual framework for the new remuneration process. Capability Analysis and Business Architecture Design: I utilized capability analysis to construct the target business architecture for the process, identifying the essential business capabilities needed to achieve the desired outcomes. Target Process Design: I meticulously designed the detailed target-state process for remuneration planning and calculation, seamlessly integrating best practices, client requirements, and our accumulated expertise. AI-Ready Process Engineering: Crucially, the process was designed from the ground up to be "AI-ready." This proactive approach ensured that key activities within the process could be easily automated by future AI agents. AI Agent Specification Development: For each identified part of the process suitable for AI application, I created detailed descriptions of the respective AI agents' functionalities, outlining their roles, input/output data, and interaction logic. Work Organization and Leadership: In my capacity as Lead Business Analyst, I was responsible for the overall organization of the work, selecting the appropriate analysis and design approach, and coordinating all project activities. Comprehensive Documentation: I prepared a complete set of project documents, including the target process description, AI agent requirements, and other necessary artifacts. | As a result of my work, the client received: A Fully Designed Target Process Description: A detailed, optimized, and agreed-upon process for remuneration planning and calculation, aligned with best practices and the company's specific needs. Ready-to-Implement AI Agent Requirements: Detailed specifications for the deployment of AI agents, enabling the automation of significant portions of the process. Preparedness for Implementation: The organization is now fully prepared to implement the new, AI-automated process. Significant Business Impact: The project laid the foundation for achieving substantial benefits: Drastic Time Savings: The process, which currently takes 11 weeks, is projected to be reduced to 1-2 weeks in the new model, representing a tenfold reduction in processing time in the best-case scenario. Reduced Errors: Minimization of human error and automation of routine operations. Decreased Human Involvement: Freeing employees from repetitive tasks, allowing them to focus on more strategic initiatives. Mitigation of Corruption Risks: Automation of calculations and payouts significantly reduces opportunities for abuse in bonus and remuneration distribution. Numerous other direct and indirect business effects enhancing process transparency and efficiency.
42 | AI Consulting | Workflow Automation | Transitrix | Enterprise Architect | Agentic AI POC | TRANS-AIPOC | Successfully demonstrated the practical applicability and value of automating the Product Development Process based on AI agents, leading to negotiations for full-scale implementation. | Transitrix |  | 2025-04-01 | 2025-09-01 | The client faced serious problems in their Product Development Process (PDP) – the process for preparing new confectionery products for the European market, as well as modernizing, changing, or retiring existing products. This process was extremely lengthy and unpredictable due to its complex, iterative nature and numerous interactions with various enterprise functions. This led to market entry delays and difficulties in managing the product lifecycle. | In my role as an Enterprise Architect, my task was to demonstrate to the client the value of automating a critical Product Development Process using artificial intelligence agents. The goal was to show the potential for significant time reduction, increased predictability, and improved transparency through analytics. The final result was to be a working Proof-of-Concept (POC) that would confirm the viability and effectiveness of this approach. | Detailed Target Process Modeling: I meticulously modeled and aligned with the client the target state of the Product Development Process, mapping complex routes, iterations, and interactions. Identification of AI Agent Automation Fragments: Based on the modeled process, specific fragments and activities that could be effectively automated with intelligent agents were identified. Development of Technical Specifications for AI Agents: Detailed technical specifications were prepared, describing the logic, functions, interactions, and requirements for each AI agent. Selection and Application of Advanced Technologies: For the POC, leading frameworks for multi-agent systems were used: Crew AI and MS Autogen. Development of a RAG (Retrieval-Augmented Generation) System: In the second phase of the project, I developed a functional RAG system for storing and retrieving the organization's knowledge about the process. POC Demonstration: I organized and conducted a demonstration of the working Proof-of-Concept, showcasing the automated process fragments and the capabilities of the RAG system. | A Working Proof-of-Concept (POC) with Agent-Based Architecture: The practical applicability and value of automating the Product Development Process based on AI agents were successfully demonstrated. Confirmed Potential for Process Acceleration: The POC showed the potential to reduce product preparation time by up to 5 times, which is critical for the client's market competitiveness. Foundation for Process Analytics: The project demonstrated the possibility of creating an analytical system that allows tracking each product at every stage of development, increasing process transparency and manageability. Client Conviction: The client was impressed with the demonstrated capabilities, which led to negotiations for a full-scale implementation of the developed approach. Technical Foundation for Scaling: The developed architectural solutions and RAG system laid a solid technical foundation for the further development and scaling of the system within the organization.
43 | Consulting | Workflow Automation | Transitrix | Enterprise Architect | EA Management | TRANS-EAM | Developed method and tooling for enterprise capability-based planning | Transitrix | Web, PHP, JS, AWS Cloud | 2019-06-01 | 2025-07-01 | Transitrix, a company specializing in developing innovative products for enterprise architecture management, identified a market need for more advanced tools for strategic planning and corporate architecture development. At the project's inception, there was a clear demand for solutions that could enhance strategic planning and the evolution of enterprise architecture. | In my role as Enterprise Architect, my primary task was the comprehensive development of a product for enterprise architecture management. This involved gathering requirements, designing the solution (a methodology and tooling for capability-based planning), and successfully launching the product into production. | To achieve these goals, I undertook the following actions throughout the project (from June 2019 to July 2025): Market Needs Analysis: Conducted an in-depth analysis of current market requirements for enterprise architecture management tools. Interviewed Enterprise Architects: Actively engaged with the target audience – enterprise architects – to identify their key pain points and expectations for the future product. Competitor Product Analysis: Researched existing competitor solutions to pinpoint their strengths and weaknesses, as well as to identify unique opportunities for our product. Formed and Recruited Development Team: Assembled and led the team responsible for the technical implementation of the product. Developed MVP (Minimum Viable Product): Designed and implemented the minimum viable version of the product, including the methodology and tooling for capability-based enterprise architecture planning. Web, PHP, JS, and AWS Cloud technologies were utilized. Early Adopter Testing: Organized and coordinated the MVP testing process with early users to gather feedback and identify areas for improvement. Developed Product Roadmap: Created a detailed three-year product roadmap outlining key milestones, functionalities, and objectives. Continuous Research and Development: Continue the process of consumer opinion research and iterative product development based on the insights gained. | As a result of my work: Methodology and Tooling Developed: A unique methodology and corresponding tooling for capability-based enterprise architecture planning have been created and implemented. MVP Product Launched: The MVP has been successfully built and is undergoing active testing by early adopters, demonstrating its functionality and alignment with core requirements. Positive Feedback Received: The product has garnered positive feedback from colleagues and early users, confirming its value and potential. Development Vector Defined: A clear three-year roadmap has been established, ensuring strategic planning for the product's future evolution. Transitrix's Competitiveness Enhanced: The product positions Transitrix as an innovative player in the enterprise architecture management market, contributing to the company's growth and development.